## Team Meetings
Team Discussions
DATE | Time Spent (hours) | What I worked on
2015-09-15 | 0.5 | Initial project discussion. Idea for proceduraly generated game. 3D RPG
2015-09-18 | 0.25 | Scrapped ambitions for 3D game, decided on 2D procedural generation.
2015-09-20 | 1 | Discussed story, art and inspirations for game.
2015-09-22 | 0.25 | Game Proposal Presentation
2015-09-29 | 0.5 | Discussion on task splitting and implementation details.
2015-10-14 | 1.5 | Setting up of online repository and issue tracker establishment
2015-10-15 | 0.5 | Online discussion on map creation.
2015-10-18 | 0.25 | Online discussion on player control
2015-10-20 | 0.25 | Online discussion on enemy types
2015-10-23 | 1.5 | Playtesting and discussion of glitches and mechanic improvement ideas
2015-10-24 | 1 | Online collaborative trouble shooting on various issues.
2015-10-27 | 0.5 | Discussion on remaining tasks and issues
2015-10-29 | 0.5 | Online discussion on Gameplay mechanics

## Provencher
DATE | Time Spent (hours) | What I worked on
2015-10-14 | 3 | Tutorials + implementation for Random map Gen
2015-10-15 | 5.5 | Implementation of Random Map Gen + Player programming
2015-10-17 | 1 | Added Exit sign to map in random room
2015-10-18 | 1.5 | Added random enemy spawning
2015-10-20 | 1.5 | Put work into enemy movement logic and gameobject communication
2015-10-22 | 2 | Drastically improved enemy spawning + enemy has flying AI
2015-10-23 | 3.5 | Lots of refactoring + Debug UI + Health + Killing Enemies + NextLevel
2015-10-24 | 2 | Improved shooting and Talos controls
2015-10-27 | 1 | Fixed crawler enemy animator + added damage from bullet generated
2015-10-30 | 2 | Bug Fixing + Game play tweaks

## Philippona
DATE | Time Spent (hours) | What I worked on

## Ningge
DATE | Time Spent (hours) | What I worked on